## Sheet1
System overview
CODE | Module | Functions | Start Date | End Date | Status
REQ_1 | User Management | Add/Update/Delete Users | 17/1/2015 | 30/1/2015
Register Account
REQ_2 | Role Management | Add/Update/Delete Roles | 17/1/2015 | 30/1/2015
Assign Role to Users
REQ_3 | Sales | Add/Update/Delete customer information | 17/1/2015 | 2015-07-02 |  | First Payment (30%)
REQ_4 | Document & Operations | Manage services information for a specific customer | 31/1/2015 | 13/2/2015
REQ_5 | Trucking & Delivery | Manage package information | 14/2/2015 | 21/2/2015
REQ_6 | Accounting | Report (Not very clear at the moment) | 22/2/2015 | 2015-07-03
Acceptance Test: | 15/3 -> 21/3(Final Payment)
Warranty: | 22/3 -> 4/4
Plan for requirment collecting
30/1/2015 | Verify user interface for the whole system
User Management
Role Management
Sales
2015-06-02 | Document & Operations
Trucking & Delivery
13/2/2015 | Accounting
27/2/2015 | Review system

## Sheet2
Sales
Import Sales
Docs | Update data | in bien ban giao hang
Trucking
Accounting

## Sheet4
1 | localization handler
2 | i18n for js
3 | change gourp main wro.xml
4 | customer added by who?
5 | uniques validation & others validation
Input vietnamese
UI icons
7 | configuration | some are not editable
date time format on UI
| max size for pdf attachment |  | LCL -> add -> FCL :bug | khong cho doi
table relationship
cascade remove
filter for each list
indexing
notification on editing approved values
database size modification
add logger
inscrease tomcat memory Pergem
link lan nhau cho tat ca cac list (new tab)
decorate button with icon
delete TEST data

## Sheet3
Import data
Tạm ứng
Rework | Sealand
Inland
Thong quan

## Sheet5
Docs
| import from excel | thong tin hai quan |  |  | tam ung: nhan vien/ke toan input
| cho phep in bien bang giao hang |  |  |  | chi: hoan ung/ chi tien mat
| ngay hang den = mien phi luu cong den + ngay | thong tin hai quan
ke toan(level) => chi phi duyet
chi phi => ke toan duyet => duyet chi phi
bang ke nha thau
| nha thau: filter: khach hang, jobno, time (cho 1 nha thau) |  | chi phi trucking co duyet ko
profit load

## Sheet6
attachment
4. Hoi lai phieu de nghi thanh toan
5. Phieu thu chi ouref
refund cho 1 job???
6. Ke hoach van tai
7. Container template